## 1 - Migration Steps Overview
Step | Step / Phase | Description (from article) | Key Outputs | Primary Owner | Supporting Roles | Target Date | Status | Notes
1 | Confirm goals and scope | Document why you are moving, which farms/site collections/file shares are in scope, and what success looks like. | Business goals; in-scope systems list; high-level timeline; success metrics (KPIs). |  | Sponsor, Project Manager |  | Not Started
2 | Run discovery and assessment | Scan existing SharePoint and file shares, capture inventory, and identify potential issues using tools like SMAT. | Inventory of farms, site collections, subsites, libraries, file shares; report of risks and blockers. |  | SharePoint Admin, Infrastructure |  | Not Started
3 | Classify and clean up content | Apply a ROT lens and decide what to migrate, archive, or delete with business owners. | Content classification (keep/archive/delete); approvals from owners; updated inventory. |  | Site Owners, Information Architect |  | Not Started
4 | Design the target environment | Design hubs, modern sites, metadata, and security model for SharePoint Online or hybrid end state. | Target information architecture; hub/site map; security model; navigation plan. |  | Information Architect, Security / Compliance |  | Not Started
5 | Plan workflow and customization modernization | Catalogue InfoPath forms, classic pages, and SharePoint workflows and decide rebuild/replace/retire. | Workflow/app catalog; modernization decisions; Power Automate / Power Apps backlog. |  | Solution Architect, Process Owners |  | Not Started
6 | Select migration tools and methods | Choose tools (SPMT/third-party) and decide cutover vs staged migration per source. | Tooling decision; runbook for each source system; credentials and access confirmed. |  | Migration Engineer, Security |  | Not Started
7 | Pilot, then migrate in waves | Run a pilot, capture lessons learned, then group remaining sites into regional/departmental waves. | Pilot results; defined waves (Pilot, W1, W2...); wave schedule; content freeze windows. |  | Project Manager, Migration Engineer, Site Owners |  | Not Started
8 | Validate, onboard, and optimize | Validate each wave, fix issues, deliver training, and drive adoption of modern experiences. | Validation reports; sign-offs; issue log; training sessions; adoption metrics. |  | Change Manager, Support, Site Owners |  | Not Started

## 2 - Plan & Checklist
Step / Phase (from article) | Workstream / Area | Task ID | Task | Subtask / Acceptance Criteria | Wave (Pilot / W1 / W2 / etc.) | Owner | Team / Role | Priority (H/M/L) | Start Date | Due Date | Status | Dependency | Comments / Notes
1. Confirm goals and scope | Business Case | 1.1 | Clarify migration drivers and success metrics | Document risk, cost, and productivity drivers; define KPIs and target dates. |  |  | Sponsor / Project Manager | H |  |  | Not Started
2. Run discovery and assessment | Inventory | 2.1 | Run discovery on existing SharePoint and file shares | Use SMAT or other tools to capture URLs, sizes, last modified dates, and owners. |  |  | SharePoint Admin | H |  |  | Not Started | 1.1
3. Classify and clean up content | Content Analysis | 3.1 | Classify content (keep/archive/delete) | ROT analysis completed with owners; decisions captured in inventory. |  |  | Information Architect / Site Owners | H |  |  | Not Started | 2.1
4. Design the target environment | Target IA | 4.1 | Design SharePoint Online information architecture | Hub/sites map, metadata, and navigation documented and reviewed. |  |  | Information Architect | H |  |  | Not Started | 3.1
5. Plan workflow and customization modernization | Workflows & Apps | 5.1 | Catalogue workflows and customizations | List InfoPath forms, classic workflows, and custom solutions; decide rebuild / replace / retire. |  |  | Solution Architect | M |  |  | Not Started | 2.1
6. Select migration tools and methods | Tooling | 6.1 | Confirm tools (SPMT/third-party) and migration mode | Tooling chosen per source; cutover vs staged defined; access tested. |  |  | Migration Engineer | H |  |  | Not Started | 4.1
7. Pilot, then migrate in waves | Pilot | 7.1 | Execute pilot migration | Pilot migrated; validation and lessons learned captured. | Pilot |  | Migration Engineer / PM | H |  |  | Not Started | 6.1
7. Pilot, then migrate in waves | Production Waves | 7.2 | Migrate remaining waves | Each wave migrated and validated; defects logged and resolved or tracked. | W1 / W2 / W3 |  | Migration Engineer / PM | H |  |  | Not Started | 7.1
8. Validate, onboard, and optimize | Validation & Adoption | 8.1 | Validate waves and deliver training | Item counts & permissions checked; sign-offs captured; training delivered. | All |  | Change Manager / Support | M |  |  | Not Started | 7.2